## Read Me
AI Governance Risk Register & Scoring Methodology
Based on FINOS AI Governance Framework (AIGF)
Risk Criteria Referenced
Purpose:
Reusable vendor-agnostic risk register. Ability to track and score risks.
Considerations: | Considerations include data, AI models, agents across lifecycles and changes
FINOS AIGF risks referenced (see link above) to make it mappable and traceable where possible
Can be used for deployment, reporting residual risk to a governance forum, etc.
Sheets | Assumptions & Considerations | Key Assumptions and considerations
| Scoring Approach | The 5x5 likelihood vs impact model, rating bands, tolerance scale, and the residual-risk / deployment-gate logic.
| Scoring Matrix | Visual 5x5 heat map plus the descriptor anchors for each likelihood and impact level.
| Risk Register | The core register: 38 risks across Operational, Security, and Regulatory domains, each with inherent & residual scoring, owner, controls, and status. (includes 23 risk criteria covered here: https://github.com/finos/ai-governance-framework/tree/main/docs/_risks)
| Lifecycle Triggers | Events that require a (re)assessment, attempted mapping to lifecycle stage and the risks each event most affects.
| Terminology Mapping | Attempted to create a shared glossary that reconciles common governance terms with FINOS / NIST / EU AI Act / OWASP language.
| Assessment Summary | Auto-rollup of counts and average scores by domain and rating, driven by the register.
| Address the Risk | Options to address risk (mitigate/transfer/remove/accept), acceptance & removal criteria (go-no-go), and the kill-switch / termination control.
Illustrative Benchmark
Gaps
Stack Coverage
Notes: | More detailed than originally intended - still evolving - this is first draft, may be simplified.
Some AI was used to accelerate the process of curating/merging content.
DRAFT

## Assumptions & Considerations
Key Assumptions and Additional Considerations
Data governance is in place, risk register does address the risk associated but most mitigation and steps will be governed by data governance
Security parameters are defined but assumption is security is implemented throughout the organization and this will be vetted against infosec parameters defined by organizational CISO
KRIs are attempted and are still being evolved
Creating a baseline is initial step regardless of maturity of the organization - key risk assessments to be done against benchmarks - this process is evolving
Considerations are still evolving for historical and future inferences
Agents make autonomous decisions and agents may use outcomes from other agents, addressing cascading agents. Transparency and linking of the risks for this is still evolving. This should include audit trail.
Snapshots of all dependencies and assumptions for any key decision points made by AI will need attention. There is a separate component being worked on for this to ensure traceability of decisions is made available to manage risks.
Risk register has an approach to addressing each risk identified, this needs to be adjusted. This will be variable as there might be more than one risk factor, it will not be a linear issue and will not have a linear solution.
A higher level framework should be the driver, the risk register is be at the playbook level where more detailed components are attempted to be addressed. Changes to regulations, business models etc. should not warrant change in framework (framework should be overarching). Playbooks may require more adjustments and should be maintained as such.
RPA is not addressed in this register.
Audit to initiate in-flight initiatives for risk register adoption TBD - will be in lifecycle triggers
DRAFT

## Scoring Approach
Scoring Approach
How inherent risk, control effectiveness, residual risk, and the deployment gate are calculated.
Inherent Risk = Likelihood (1-5) vs Impact (1-5)
Inherent risk is the exposure before mitigating controls are credited. Score Likelihood and Impact independently on the 1-5 anchors below, then multiply. The product ranges from 1 to 25 and maps to a four-tier rating band.
Likelihood
Level | Level Rating | Description
1 | Rare | May occur only in exceptional circumstances, no known occurrence in similar systems.
2 | Unlikely | Could occur but not expected, isolated instances of precedence in the industry.
3 | Possible | Might occur at some point, has happened in similar AI deployments.
4 | Likely | Expected to occur in most circumstances within the assessment period.
5 | High Probability (Certainty) | Expected to occur frequently / continuously when there is not addressed.
Impact
Level | Level Rating | Description
1 | Insignificant | Negligible effect, no customer harm, no regulatory interest, easily absorbed.
2 | Minor | Limited, contained harm, minor remediation, no reportable breach.
3 | Moderate | Noticeable customer / operational harm, possible regulatory attention, manageable cost.
4 | Major | Significant harm, financial loss, or compliance breach, senior escalation, reportable.
5 | Severe | Systemic harm, large fines, license / reputational damage, or safety impact at scale.
Rating Bands
Range | Rating | Governance Consideration
1 – 4 | Low | Acceptable with baseline controls and routine oversight.
5 – 9 | Moderate | Acceptable with standard guardrails, monitoring, and periodic review.
10 – 15 | High | Deploy only with mandatory controls, approval gates, and active monitoring.
16 – 25 | Critical | Do not deploy as-is, redesign to reduce exposure or require human-in-the-loop. Go-no-go. (if deployed - Kill)
Control effectiveness and Rating Bands
Rate the effectiveness of existing controls on a 1-5 scale (1 = Ineffective through 5 = Fully effective). reduces exposure
Residual Score = Inherent Score × Mitigation Factor, where the increase in controls reduce exposure.
Governance forum reviews and escalates/makes decision on residual risk.
Level | Effectiveness Level Rating | Implication | Mitigation Factor | Residual = Inherent × Mitigation factor
1 | Ineffective | Controls absent or untested | 1.00 | 100%
2 | Limited | Partial / ad-hoc controls | 0.80 | 80%
3 | Moderate | Standard controls, some gaps | 0.60 | 60%
4 | Strong | Robust, tested controls | 0.40 | 40%
5 | Fully effective | Comprehensive, continuously assured | 0.25 | 25%
Risk Tolerance Deployment Gate (go-no-go)
Residual Rating | Tolerance Stance | Rating | Gate Decision | Required Sign-off
Low | Accept | PASS | Proceed | Product / risk owner
Moderate | Accept w/ monitoring | PASS | Proceed with conditions | AI governance lead
High | Mitigate before deploy | CONDITIONAL | Controls must close gap | Governance forum / CRO delegate
Critical | Avoid / redesign | FAIL | Block deployment/Kill | Governance forum + accountable executive
DRAFT

## Risk Register
AI Governance Risk Register
ID | FINOS Ref (if available) | Domain | Risk | Description | Potential Impact | Likelihood | Impact | Inherent | Threshold (determined by use case/context) | Inherent Rating | Existing Controls | Ctrl Effectiveness | Residual | Residual Rating | Treatment | Owner | Status | FINOS Coverage | Stack Layer
R-01 | ri-4 | Operational | Hallucination & Inaccurate Outputs | Model generates confident but fabricated or incorrect information not grounded in fact, RAG reduces but cannot eliminate it. | Poor decisions, fabricated financial data/advice, customer harm, mis-statement in regulated outputs. | 3 | 5 | 15 |  | High | RAG grounding, human-in-the-loop on material outputs, output validation, confidence thresholds. | 3 | 9 | Moderate | Mitigate | Head of Data Science | In Progress | FINOS | L9
R-02 | ri-5 | Operational | Foundation Model Versioning | Silent or unmanaged upstream model/version changes alter behavior and break prior validation and reproducibility. | Untracked behavioral drift, broken testing, compliance/audit gaps. | 3 | 4 | 12 |  | High | Version pinning, change notification SLAs, regression test suite on version change. | 3 | 7 | Moderate | Mitigate | ML Platform Lead | In Progress | FINOS | L6
R-03 | r1_6 | Operational | Non-Deterministic Behavior | Identical inputs can yield different outputs due to probabilistic sampling, complicating testing and assurance. | Inconsistent customer experience, unreliable compliance checks, hard-to-reproduce defects. | 3 | 3 | 9 |  | Moderate | Temperature/seed control where supported, tolerance-based test assertions, output logging. | 3 | 5 | Moderate | Mitigate | ML Platform Lead | Planned | FINOS | L7
R-04 | ri-7 | Operational | Availability of Foundation Model | Dependence on third-party GPU-hosted models creates outage, throttling, Denial-of-Wallet and VRAM-exhaustion exposure. | Service disruption, cost spikes, business-continuity breach. | 3 | 4 | 12 |  | High | Multi-provider failover, rate limiting, capacity planning, usage monitoring & alerts. | 3 | 7 | Moderate | Mitigate | Head of AI Engineering | In Progress | FINOS | L3
R-05 | r1-14 | Operational | Inadequate System Alignment | RAG/agent outputs diverge from intended business purpose or compliance constraints despite appearing relevant. | Regulatory violations, customer harm, scaled operational error. | 3 | 4 | 12 |  | High | System-acceptance testing, scope guardrails, prompt templates, continuous response-quality monitoring. | 3 | 7 | Moderate | Mitigate | Head of AI Governance | Planned | FINOS | L9
R-06 | ri-16 | Operational | Bias & Discrimination | Systems disadvantage protected groups via skewed data, proxies, or feedback loops (e.g. credit, fraud, pricing). | Fair-lending breach, discriminatory outcomes, regulatory penalty, reputational damage. | 3 | 5 | 15 |  | High | Bias testing on protected attributes, fairness metrics, diverse data review, human review of high-impact decisions. | 3 | 9 | Moderate | Mitigate | Head of AI Governance | In Progress | FINOS | L7
R-07 | ri-17 | Operational | Lack of Explainability | Black-box decisions cannot be adequately interpreted or justified to regulators, stakeholders, or customers. | Reduced trust, inability to contest decisions, regulatory non-compliance. | 3 | 4 | 12 |  | High | Model documentation, explainability tooling, user-facing disclosures, decision logging. | 3 | 7 | Moderate | Mitigate | Head of AI Governance | Planned | FINOS | L6
R-08 | ri-18 | Operational | Model Overreach / Expanded Use | A model is used beyond its validated scope or intended purpose, often due to over-trust / anthropomorphism. | Non-compliant outputs, unsuitable advice, operational error in high-stakes tasks. | 3 | 4 | 12 |  | High | Approved use-case registry, scope constraints, user training, periodic use review. | 3 | 7 | Moderate | Mitigate | Head of AI Governance | Planned | FINOS | L6
R-09 | ri-19 | Operational | Data Quality & Drift | Outdated or poor-quality data and concept drift erode accuracy over time (model aging). | Flawed risk assessments, stale compliance logic, degraded decisions. | 3 | 4 | 12 |  | High | Data-quality monitoring, scheduled revalidation/retraining, drift detection, lineage controls. | 3 | 7 | Moderate | Mitigate | Head of Data Governance | In Progress | FINOS | L5
R-10 | ri-20 | Operational | Reputational Risk | Customer-facing AI failures scale rapidly into public incidents that erode brand and trust. | Media backlash, customer attrition, regulatory scrutiny, brand damage. | 3 | 4 | 12 |  | High | Guardrails on customer-facing outputs, incident response playbook, pre-release red-teaming. | 3 | 7 | Moderate | Mitigate | Chief Risk Officer | Planned | FINOS | L10
R-11 | ri-28 | Operational | Multi-Agent Trust Boundary Violations | Compromise in one agent propagates across a multi-agent system via shared state or communication channels. | Cascading failures, cross-function impact, amplified loss, complex incident response. | 2 | 5 | 10 |  | High | Agent isolation, inter-agent authN/authZ, shared-resource controls, cross-agent monitoring. | 2 | 8 | Moderate | Mitigate | Head of AI Governance | Planned | FINOS | L8
R-12 | ri-1 | Security | Information Leaked to Hosted Model | Sensitive data sent to a third-party hosted model may be memorized, logged, or exposed (incl. cross-user leakage). | PII/PHI exposure, IP loss, GDPR/GLBA breach, regulatory fines. | 4 | 5 | 20 |  | Critical | Enterprise no-train agreements, input filtering/redaction, private endpoints, DLP on prompts. | 3 | 12 | High | Mitigate | Chief Privacy Officer | In Progress | FINOS | L4
R-13 | ri-2 | Security | Information Leaked to Vector Store | Confidential data embedded in a vector store can be reconstructed via inversion or membership-inference attacks. | Reconstruction of sensitive data, confidentiality breach, poisoning. | 3 | 4 | 12 |  | High | Embedding access controls (RBAC), encryption at rest, pre-embedding data filtering, audit logging. | 3 | 7 | Moderate | Mitigate | Chief Information Security Officer | In Progress | FINOS | L5
R-14 | ri-8 | Security | Tampering with the Foundation Model | Model supply chain (weights, training data, firmware, ML libs) compromised, poisoned, or back-doored upstream. | Backdoors, unsafe behavior under triggers, integrity loss. | 2 | 5 | 10 |  | High | Provenance checks, trusted providers, tamper-detection, SBOM for ML dependencies. | 2 | 8 | Moderate | Mitigate | Chief Information Security Officer | Planned | FINOS | L6
R-15 | ri-9 | Security | Data Poisoning | Adversaries tamper with training/fine-tuning/retrieval data to manipulate model behavior, often subtly. | Biased decisioning, fraud approval, degraded performance, hidden failures. | 2 | 5 | 10 |  | High | Source validation, third-party feed integrity checks, anomaly detection, continuous-learning safeguards. | 2 | 8 | Moderate | Mitigate | Chief Information Security Officer | Planned | FINOS | L5
R-16 | ri-10 | Security | Prompt Injection | Crafted direct or indirect inputs override instructions to leak data or trigger unintended actions. | Data leakage, unsafe automated actions, misinformation, reputational harm. | 4 | 4 | 16 |  | Critical | Input/output firewalling, LLM-as-judge, indirect-injection scanning of ingested content, least privilege. | 3 | 10 | High | Mitigate | Chief Information Security Officer | In Progress | FINOS | L8
R-17 | ri-24 | Security | Agent Action Authorization Bypass | Agents act beyond authorized scope — discovering APIs, chaining tools, or circumventing approval workflows. | Unauthorized transactions, segregation-of-duties breach, regulatory violation. | 3 | 5 | 15 |  | High | Granular per-agent RBAC, tool-manager authZ, approval gates, segregation-of-duties enforcement. | 2 | 12 | High | Mitigate | Head of AI Governance | Planned | FINOS | L8
R-18 | ri-25 | Security | Tool Chain Manipulation & Injection | Inputs manipulate an agent's tool selection or inject malicious parameters into legitimate API calls. | Payment redirection, data exfiltration, compliance bypass, fraud. | 3 | 5 | 15 |  | High | Tool-selection validation, parameter sanitization, constrained tool scopes, sequence monitoring. | 2 | 12 | High | Mitigate | Chief Information Security Officer | Planned | FINOS | L8
R-19 | ri-26 | Security | MCP Server Supply Chain Compromise | Compromised Model Context Protocol servers feed agents tainted data, logic, or capabilities at scale. | Systematic decision corruption, credential harvesting, widespread compliance failure. | 3 | 5 | 15 |  | High | MCP server vetting, pre-approved server registry, signed/encrypted MCP comms, response monitoring. | 2 | 12 | High | Mitigate | Head of AI Governance | Planned | FINOS | L1
R-20 | ri-27 | Security | Agent State Persistence Poisoning | Malicious instructions persist in agent memory across sessions, creating long-lived backdoors. | Persistent fraud bypass, systematic compliance violation, accumulated loss. | 2 | 5 | 10 |  | High | State validation/sanitization, memory access controls, state-change auditing, session isolation. | 2 | 8 | Moderate | Mitigate | Head of AI Governance | Planned | FINOS | L8
R-21 | ri-29 | Security | Agent-Mediated Credential Harvesting | Agents are exploited to discover and exfiltrate credentials, API keys, and secrets across systems. | Infrastructure-wide compromise, lateral movement, large-scale breach. | 2 | 5 | 10 |  | High | Credential segmentation from agent runtime, secrets-vault isolation, tool restrictions, access-pattern monitoring. | 2 | 8 | Moderate | Mitigate | Chief Information Security Officer | Planned | FINOS | L8
R-22 | ri-22 | Regulatory | Regulatory Compliance & Oversight | AI systems must meet the same obligations as human-driven processes, evolving regimes (EU AI Act, SR 11-7, SS1/23) raise the bar. | Fines, enforcement, restrictions, legal action, mandated remediation. | 3 | 5 | 15 |  | High | Use-case-to-regulation mapping, model governance & validation, record-keeping, FRIA for high-risk uses. | 3 | 9 | Moderate | Mitigate | Chief Compliance Officer | In Progress | FINOS | L6
R-23 | ri-23 | Regulatory | Intellectual Property & Copyright | Training data or outputs may infringe IP, or staff may leak trade secrets into public AI tools. | Infringement claims, trade-secret loss, licensing breach, contractual liability. | 3 | 4 | 12 |  | High | Vendor IP indemnity, acceptable-use policy, output IP screening, DLP on public tools. | 3 | 7 | Moderate | Mitigate | General Counsel | Planned | FINOS | L6
R-24 | ri-1 | Regulatory | Information Leaked To Hosted Model - Data Protection & Privacy Compliance | Failure to meet GDPR/CCPA/GLBA data-subject rights and purpose-limitation in AI processing of PII/PHI. | Privacy fines, data-subject complaints, mandated deletion, reputational harm. | 3 | 5 | 15 |  | High | Data minimization, DPIAs, lawful-basis mapping, retention controls, data-subject-rights workflow. | 3 | 9 | Moderate | Mitigate | Chief Privacy Officer | In Progress | FINOS | L4
R-25 | ri-18 | Agent Operations | Model Overreach / Expanded Use - Autonomous Decision-Making Beyond Mandate | An agent makes and executes decisions independently that should require human judgement or fall outside its approved decision rights, due to over-broad autonomy or ambiguous scope. | Unauthorized or unreviewed actions, decisions made without accountability, regulatory and financial exposure. | 3 | 5 | 15 |  | High | Defined decision-rights matrix, autonomy tiering (suggest/approve/auto), approval gates on sensitive actions, full action audit log, KILL-SWITCH on out-of-mandate actions. | 2 | 12 | High | Mitigate | Head of AI Governance | Planned | FINOS-adjacent | L8
R-26 | ri-14?? Alignment tbd | Agent Operations | Outcome Deviation & Detection Gap | An agent's outputs drift from expected/normalized outcomes and the deviation is not detected promptly because monitoring lacks an outcome baseline, or the agent self-reports success while producing wrong results. | Silent accumulation of wrong outcomes, delayed detection, eroded trust, scaled error before intervention. | 3 | 4 | 12 |  | High | Outcome baselining vs golden datasets, continuous deviation monitoring & alerting, independent (non-self-reported) validation, canary checks, auto-pause on threshold breach. | 2 | 10 | High | Mitigate | ML Platform Lead | Planned | FINOS-adjacent | L9
R-27 | ri-6/ri-19? Align agentic | Agent Operations | DQ issues/non-deterministic behavior. Pattern-Shift Rejected as Anomaly | When a genuine, legitimate shift in data distribution occurs (a new normal / pattern shift, not a one-off anomaly), the agent rejects the data as anomalous and fails to adapt continuing to act on outdated normalized values. | Agent operates on stale assumptions, rejects valid inputs, produces systematically wrong results during regime change. | 3 | 4 | 12 |  | High | Distinguish drift vs anomaly (trend vs outlier tests), human review of sustained 'anomaly' clusters, adaptive thresholds, scheduled re-baselining, escalation when rejection rate spikes. | 2 | 10 | High | Mitigate | Head of Data Science | Planned | GAP | L5
R-28 | ri-4/ri/14? | Agent Operations | hallucination/inadequate system alignment, Fabricated Outcome Under Inability to Respond | When an agent cannot generate a valid response (missing data, tool failure, low confidence) it guesses or fabricates an outcome instead of failing safe or escalating — masking the gap as a confident result. | Fabricated decisions enter downstream processes, false confidence, undetected wrong outputs in regulated workflows. | 4 | 5 | 20 |  | Critical | Mandatory confidence thresholds with fail-safe/abstain path, 'I-don't-know' escalation route, tool-failure handling that halts not guesses, output provenance & confidence logging, KILL-SWITCH on repeated low-confidence fabrication. | 2 | 16 | Critical | Mitigate | Head of AI Governance | Planned | GAP | L9
R-29 | ri-25/ri-28?? | Agent Operations | Toolchain / injection/boundary violations Cascading Deviation in Connected Agents (No Rollback) | One agent depends on another agent's outcome, a dependent agent receives corrupt, skewed, or fabricated input and propagates it, creating a sequence of deviations that is hard to detect and has no rollback plan to a known-good state. | Compounding errors across the chain, unrecoverable state, systemic failure, very high detection difficulty. | 3 | 5 | 15 |  | High | Inter-agent input validation & contracts, provenance/lineage tagging across hops, circuit-breakers between agents, transactional checkpoints with rollback/compensation, chain-level kill-switch, MANDATORY pre-release review for connected-agent chains. | 2 | 12 | High | Mitigate | Head of AI Governance | Planned | FINOS-adjacent | L8
R-30 | ri-28/ri-6?? | Agent Operations | non-deterministic behavior/boundary violations/Result Skew from Upstream Agent Non-Response | An upstream agent is unable to generate a response (timeout, failure, empty output), the dependent agent proceeds on incomplete/default input, skewing its own result rather than halting. | Skewed downstream decisions, silent degradation of the whole chain, masked single-point failure. | 3 | 4 | 12 |  | High | Explicit handling of null/empty/timeout upstream results, fail-closed defaults, dependency health checks, require positive acknowledgement before proceeding, degrade-gracefully vs proceed-blindly policy. | 2 | 10 | High | Mitigate | ML Platform Lead | Planned | FINOS-adjacent | L8
R-31 | ri-27? | Agent Operations | Agent state persistence posioningCorrupt-Input Propagation Across Agent Trust Boundary | A dependent agent implicitly trusts an upstream agent and ingests corrupt or poisoned input without revalidation, allowing corruption to cross the trust boundary and skew or poison the dependent agent's reasoning or state. | Cross-agent corruption, poisoned state, manipulated decisions propagated as trusted, broad blast radius. | 2 | 5 | 10 |  | High | Zero-trust between agents (revalidate every hop), schema & sanity checks on inter-agent payloads, signed/attested messages, isolate agent state, anomaly detection on inter-agent traffic. | 2 | 8 | Moderate | Mitigate | Chief Information Security Officer | Planned | GAP | L8
R-32 | ? | Infrastructure & Supply | Compute Supply Chain & Concentration | GPU/accelerator shortage, single-vendor or single-region dependency, or capacity unavailability constrains training/inference and creates cost and continuity exposure at the hardware layer (L1). | Inability to train/serve, runaway cost, business continuity breach, strategic dependency. | 3 | 4 | 12 |  | High | Multi-vendor/region sourcing, reserved capacity & commitments, demand forecasting, FinOps controls, fallback to alternate accelerators. | 2 | 10 | High | Mitigate | Chief Technology Officer | Planned | GAP | L1
R-33 | ? | Infrastructure & Supply | Infrastructure Resilience & DR Gap | GPU node failure, network partition, region outage, or absent/untested disaster recovery for AI platform components (L2-L3) disrupts model availability and breaks continuity expectations. | Service outage, failed failover, SLA/continuity breach, data-in-flight loss. | 2 | 4 | 8 |  | Moderate | HA cluster design, tested DR runbooks, multi-AZ/region failover, chaos/resilience testing, RTO/RPO targets for AI services. | 2 | 6 | Moderate | Mitigate | Head of AI Engineering | Planned | GAP | L2
R-34 | ? | Infrastructure & Supply | Cloud Cost Overrun & FinOps Gap (Denial-of-Wallet) | Uncontrolled token/inference spend, runaway agent loops, or unmonitored GPU utilization drive cost overruns, absent FinOps translation layer between finance and infra (L3). | Budget overrun, untracked spend, throttling, ROI erosion. | 4 | 3 | 12 |  | High | Per-use-case API keys & quotas, spend alerts & budgets, utilization monitoring, rate limiting, agent step/cost caps (links kill-switch). | 2 | 10 | High | Mitigate | Chief Financial Officer / FinOps | Planned | GAP | L3
R-35 | ? | Infrastructure & Supply | Vendor Lock-in & Concentration | Tight coupling to a single model provider, cloud, or platform limits failover, pricing leverage, and portability (L3), concentration risk if that provider degrades or changes terms. | Reduced resilience, pricing exposure, migration cost, strategic dependency. | 3 | 3 | 9 |  | Moderate | Abstraction/gateway layer over providers, portability standards, contractual exit terms, periodic alternative-provider evaluation. | 2 | 7 | Moderate | Mitigate | Chief Technology Officer | Planned | GAP | L3
R-36 | ri-19?? | Data Pipeline | Data drift/Training-Serving Skew & Feature Pipeline Drift | Feature distributions at serving diverge from training (training-serving skew), or pipeline transformations differ between offline and online paths, silently degrading model accuracy (L5). | Silent accuracy loss, wrong decisions, hard-to-detect degradation. | 3 | 4 | 12 |  | High | Shared feature definitions / feature store, skew monitoring (PSI/KS), offline-online parity tests, pipeline versioning. | 2 | 10 | High | Mitigate | Head of Data Science | Planned | FINOS-adjacent | L5
R-37 | ? | Data Pipeline | Data Lineage & Provenance Gap | Missing or incomplete lineage means the origin, consent basis, transformations, and downstream use of training/feature data cannot be traced — blocking impact analysis, erasure, and audit (L5). | Unauditable data, blocked right-to-erasure, undetected poisoning, compliance failure. | 3 | 4 | 12 |  | High | End-to-end lineage capture, dataset/version registry, consent & license tagging, provenance attestation, lineage in DPIA. | 2 | 10 | High | Mitigate | Head of Data Governance | Planned | GAP | L5
R-38 | ? | Business Outcome | Strategic Misalignment & Failed ROI | AI investment fails to deliver expected business value, or use cases drift from strategy, benefits unrealized relative to spend, eroding executive confidence and funding (L10). | Wasted investment, lost confidence, defunding, opportunity cost. | 3 | 4 | 12 |  | High | Value-tracking vs business case, benefits realization reviews, portfolio prioritization, outcome KPIs tied to AI strategy pillars. | 3 | 7 | Moderate | Mitigate | Chief Data & Analytics Officer | Planned | GAP | L10
DRAFT

## Scoring Matrix
Scoring Matrix — Likelihood × Impact Heat Map
Score = Likelihood (rows) × Impact (columns). Colors show the rating bands.
Likelihood | IMPACT |  |  |  |  | LIKELIHOOD increases downward, IMPACT increases rightward.
| 1 | 2 | 3 | 4 | 5
1 | 1 | 2 | 3 | 4 | 5
2 | 2 | 4 | 6 | 8 | 10
3 | 3 | 6 | 9 | 12 | 15
4 | 4 | 8 | 12 | 16 | 20
5 | 5 | 10 | 15 | 20 | 25
Legend
1 – 4 | Low | Baseline controls, routine oversight.
5 – 9 | Moderate | Standard guardrails + monitoring.
10 – 15 | High | Mandatory controls + approval gate.
16 – 25 | Critical | Block / redesign / human-in-the-loop.

## Lifecycle Triggers
Lifecycle Triggers — When to (Re)assess
Lifecycle Stage | Trigger / Event | Required Action | Risks Most Affected
Onboarding / Intake | New AI use case proposed or new model/vendor introduced | Run full register assessment, classify data & autonomy, set initial tolerance | All — establishes baseline
Onboarding / Intake | Use case involves PII/PHI or confidential data | Trigger DPIA, score privacy & leakage risks, legal review | R-12, R-13, R-24, R-23
Design / Build | Architecture adds RAG, vector store, or external knowledge base | Assess embedding leakage & data-filtering controls | R-13, R-05, R-09
Design / Build | Agentic capability, tool use, or MCP servers introduced | Score full agentic risk set, define scoped permissions & approval gates | R-11, R-17, R-18, R-19, R-20, R-21
Pre-Deployment Gate | Readiness for production sign-off | System-acceptance testing, residual scoring, gate decision vs tolerance | All applicable
Pre-Deployment Gate | High-risk classification under EU AI Act (e.g. credit, fraud) | Fundamental Rights Impact Assessment, enhanced documentation | R-06, R-07, R-22, R-24
Draft In progress

## Terminology Mapping
Common Term | Definition (plain language) | Equivalent / Related Terms | Reference
Inherent Risk | Exposure before mitigating controls are credited. | Gross risk, pre-control risk | ISO 31000, NIST
Residual Risk | Exposure remaining after controls are applied. | Net risk, managed risk
Likelihood | Probability the risk event occurs in the assessment period. | Probability, frequency
Impact | Severity of consequence if the event occurs. | Consequence, severity, magnitude
Risk Rating | Band (Low/Moderate/High/Critical) derived from the score. | Risk level, severity tier
Risk Tolerance | Level of residual risk the organisation will accept. | Risk appetite, acceptance threshold
Deployment Gate | Go/no-go control point comparing residual risk to tolerance. | Release gate, approval gate, stage gate
Hallucination | Confident but fabricated/incorrect model output. | Confabulation, ungrounded output
Model Drift | Decline in performance as data diverges from training. | Concept drift, data drift, model aging
Explainability | Ability to interpret and justify a model's decisions. | Interpretability, transparency
Prompt Injection | Crafted input overriding intended model instructions. | Jailbreak (direct), indirect injection
Data Poisoning | Tampering with training/retrieval data to corrupt behaviour. | Training-data attack
Excessive Agency | Agent acting beyond intended authority or scope. | Authorization bypass, over-permissioning
Agentic AI | AI that plans, decides, and acts autonomously via tools. | Autonomous agent, tool-using agent
MCP | Model Context Protocol standard for extending agent tools/data. | Tool server, context server
Tool Chain | Sequence of tools/APIs an agent invokes to complete a task. | Action chain, tool orchestration
Trust Boundary | Point where data/control crosses between trust zones. | Security boundary, isolation boundary
Human-in-the-Loop | Human review/approval inserted into the decision flow. | HITL, human oversight
DPIA | Data Protection Impact Assessment for privacy risk. | Privacy impact assessment (PIA)
FRIA | Fundamental Rights Impact Assessment for high-risk AI. | Rights impact assessment
Model Risk Management | Governance of model development, validation, monitoring. | MRM, model governance
Control Effectiveness | How well existing controls reduce the inherent risk. | Control maturity, mitigation strength

## Address the Risk
Addressing the Risk & Acceptance Criteria
How each register risk is treated, and the explicit criteria for mitigating, removing, or accepting it.
Options to address
Option | What it means | When to choose it
Mitigate / Reduce | Apply or strengthen controls to lower likelihood and/or impact until residual risk is within tolerance. | Default for most High/Critical risks where the use case has clear business value and controls can close the gap.
Transfer | Shift exposure to a third party — contractual indemnity, insurance, or vendor-assumed liability. | Where another party is better positioned to bear or control the risk (e.g. model provider indemnity for IP).
Avoid / Remove | Eliminate the exposure by removing the capability, decommissioning the model/agent, or not deploying. | Where residual risk stays Critical after mitigation, or cost/effort outweighs value. Triggers removal criteria below.
Accept | Formally accept the residual risk with documented sign-off and ongoing monitoring. | Where residual risk is within tolerance and meets the acceptance criteria below.
Acceptance Criteria (all must hold to accept)
Residual rating is within the organization's stated tolerance for the use-case tier (typically Low or Moderate).
All credible mitigations have been applied or consciously deferred with rationale, no quick win is left undone.
An accountable owner is named, and the required sign-off level (per the deployment gate) has been obtained.
Monitoring and trigger conditions are defined so the acceptance is revisited if exposure changes.
A review/expiry date is set — acceptance is time-bound, not permanent.
Acceptance is documented in the register (Address Risk = Accept, Status = Accepted) with date and approver.
RISK REMOVAL / AVOIDANCE CRITERIA (any one may trigger removal)
Residual rating remains Critical after all reasonable mitigation, and human-in-the-loop cannot reduce it.
The risk cannot be detected or rolled back reliably (e.g. cascading multi-agent deviation with no recovery path).
Mitigation cost or operational drag outweighs the use case's business value.
A legal, regulatory, or ethical constraint prohibits the capability as designed.
Acceptance criteria cannot be met and no owner will accept the residual risk.
KILL-SWITCH / COMPLETE TERMINATION (control of last resort) - need authorization chain defined
A kill-switch is a pre-defined, tested mechanism to immediately halt an AI system or agent — pausing a single agent, breaking a connected-agent chain, or fully terminating the deployment — and fail to a safe, known state. It is a required control for any system rated High or Critical residual, for all autonomous-action agents, and for all connected-agent chains. It must be tested before release and exercised periodically.
Possible approach
Invocation Trigger | Scope of Action | Owner / Authority
Out-of-mandate autonomous action detected | Pause the offending agent, revoke action privileges | On-call governance / SecOps
Outcome deviation breaches threshold | Auto-pause agent, route to human, freeze outputs | Automated + ML Platform Lead
Repeated low-confidence or fabricated outputs | Halt agent, force fail-safe/abstain, alert | Automated + AI Governance
Cascading deviation across connected agents | Break the chain at circuit-breaker, isolate state, roll back to checkpoint | Automated + Governance forum
Corrupt input crossing agent trust boundary | Quarantine payload, suspend dependent agents | SecOps
Security incident (injection, poisoning, credential) | Terminate affected agents, revoke credentials | CISO / SecOps
Regulatory or legal direction to stop | Complete termination of the deployment | Accountable executive

## Illustrative Benchmark
Benchmarks — Define, Measure, Reassess
A benchmark is a target threshold for a section (domain) or a lifecycle stage. Set the target, record the current measured value, and the Status auto-flags whether it is Met or a Gap. Reassess on the stated cadence.
How benchmarking works
1. Define a measurable target per section and per stage (e.g. 'avg residual ≤ 8', 'gate pass-rate ≥ 90%'). 2. Record the current value from the register or your monitoring. 3. Status compares the two against the target direction. 4. Reassess each benchmark on its cadence, and whenever a lifecycle trigger fires. Benchmarks are versioned — capture the baseline date so drift in the benchmark itself is visible.
SECTION BENCHMARKS (per domain)
Section / Domain | Benchmark Metric | Target | Current | Status | Reassess Cadence | Owner
Operational | Avg residual score ≤ target | 8 |  |  | Quarterly | Head of AI Governance
Security | Avg residual score ≤ target | 8 |  |  | Quarterly | CISO
Regulatory | Avg residual score ≤ target | 7 |  |  | On reg change | Chief Compliance Officer
Agent Operations | Avg residual score ≤ target | 8 |  |  | Monthly | Head of AI Governance
Infrastructure & Supply | Avg residual score ≤ target | 8 |  |  | Quarterly | Chief Technology Officer
Data Pipeline | Avg residual score ≤ target | 7 |  |  | Monthly | Head of Data Governance
Business Outcome
All sections | Open FINOS gaps not yet reviewed = target |  |  |  | Continuous | Head of AI Governance

## Gaps
Gap Register — Risks Not Addressed by FINOS AIGF
Gap ID | Gap / Missing Risk | How Surfaced | Why FINOS Doesn't Cover It | Disposition | Register ID | Date Added | Reassess (suggestions?)
G-01 | Pattern-Shift Rejected as Anomaly | Benchmark review — drift metric flagged sustained 'anomaly' clusters | FINOS r-19 covers drift/decay but not the agent actively rejecting a legitimate new-normal as an outlier and failing to adapt. | Added to register | R-27 | 2026-06-30 | Quarterly
G-02 | Fabricated Outcome Under Inability to Respond | Incident review — agent returned confident output despite tool failure | FINOS r-4 covers hallucination generally, this is the specific fail-open behavior of guessing instead of abstaining/escalating when unable to answer. | Added to register | R-28 | 2026-06-30 | Quarterly
G-03 | Corrupt-Input Propagation Across Agent Trust Boundary | Pre-release review of a connected-agent chain | FINOS r-27 / OP-028 address state poisoning and multi-agent boundaries, this captures a dependent agent implicitly trusting upstream output and skipping revalidation. | Added to register | R-31 | 2026-06-30 | Per release
G-04 | Compute Supply Chain & Concentration | Stack-coverage validation (L1) | FINOS scope is model/data/agent, not hardware-layer GPU supply or vendor concentration. | Added to register | R-32 | 2026-06-30 | Quarterly
G-05 | Infrastructure Resilience & DR Gap | Stack-coverage validation (L2) | No FINOS risk covers GPU node failure, network partition, or AI-platform disaster recovery. | Added to register | R-33 | 2026-06-30 | Quarterly
G-06
G-07 | Data Lineage, Skew & Strategic ROI | Stack-coverage validation (L5, L10) | Training-serving skew, lineage/provenance, and business-outcome/ROI risk extend beyond FINOS's model-centric catalogue. | Added to register | R-36, R-37, R-38 | 2026-06-30 | Quarterly
Refer to #296 for Stack coverage https://github.com/finos/ai-governance-framework/issues/296

## Stack Coverage
Stack Coverage Validation — Register vs Business / Technology Architecture (see document mapping in issue #296) https://github.com/user-attachments/files/28842813/AIGovernnaceFramework-FINOS-draft.pdf
Validates the risk register against the 10-layer AI stack and its parallel business architecture. For each layer: the business function, the technology layer, the layer-level risk the architecture asserts, the register risks that cover it, and a coverage verdict. Gaps closed by new risks R-32 to R-38 are marked.
Layer | Business Function | Technology Layer | Architecture Risk (asserted) | Register Coverage | Verdict | New Risk
L10 | Business outcome (revenue, NPS, ROI) | End user (chat, voice, API) | Reputational & strategic risk — brand, failed ROI, trust | R-10 Reputational (operational) | Partial → Closed | R-38
L9 | Product & UX (features, journeys) | Application (app logic, UX shell) | UX & hallucination risk — harmful outputs, over-reliance, UI bias | R-01, R-05, R-06, R-27, R-29 | Covered | —
L8 | Integration & workflow (automation) | API & orchestration (RAG, agents) | Security & integration risk — prompt injection, API abuse, agent runaway | R-11, R-16-22, R-25, R-30-31 | Covered | —
L7 | AI capability (model selection) | Inference & serving (vLLM, KServe) | Model performance & bias risk — drift, accuracy decay, discriminatory output | R-03, R-06 | Covered | —
L6 | Governance & risk (ethics, audit) | Model layer (weights, fine-tuning) | Regulatory & compliance risk — EU AI Act, GDPR, explainability | R-02, R-07, R-08, R-14, R-22-23 | Covered | —
L5 | MLOps & delivery (lifecycle, CI/CD) | ML frameworks (PyTorch, JAX) | DATA RISK — training & pipeline: poisoned data, skew, stale labels, lineage gaps | R-09, R-13, R-15 | Partial → Closed | R-36, R-37
L4 | Data strategy (products, contracts) | Acceleration libraries (CUDA, TensorRT) | DATA RISK — quality & privacy: PII leakage, consent gaps, contract breaches | R-12, R-24 | Covered | —
L3 | Cloud & platform (CapEx, OpEx, vendors) | OS & virtualization (Linux, K8s) | Operational & vendor risk — lock-in, cost overrun, SLA breach | R-04 (availability only) | Gap → Closed | R-34, R-35
L2 | Infra operations (SRE, reliability) | Firmware & drivers (CUDA driver, ROCm) | Infrastructure & resilience risk — GPU failure, network partition, DR gaps | — (none) | Gap → Closed | R-33
L1 | Compute investment (GPU, cloud spend) | Hardware (GPU, CPU, HBM) | Supply chain & concentration risk — GPU shortage, single-vendor, cost | R-19 (MCP supply only) | Gap → Closed | R-32
GAP LIST — exposures asserted by the architecture but absent / partial in the register (now closed)
New ID | Layer | Gap Closed | Why It Was Missing |  | Domain Added
R-32 | L1 | Compute supply chain & concentration | FINOS focuses on model/data/agent risk, not hardware-layer GPU supply or vendor concentration. |  | Infrastructure & Supply
R-33 | L2 | Infrastructure resilience & DR gap | No FINOS risk covers GPU node failure, network partition, or AI-platform DR. |  | Infrastructure & Supply
R-34 | L3 | Cloud cost overrun & FinOps (Denial-of-Wallet) | Cost/FinOps exposure sits outside FINOS, only availability (AIR-OP-007) is partial. |  | Infrastructure & Supply
R-35 | L3 | Vendor lock-in & concentration | Provider/cloud lock-in and portability not addressed as a discrete FINOS risk. |  | Infrastructure & Supply
R-36 | L5 | Training-serving skew & feature drift | FINOS AIR-OP-019 covers drift broadly, serving skew & feature-pipeline parity are specific extensions. |  | Data Pipeline
R-37 | L5 | Data lineage & provenance gap | Lineage/provenance as an auditable control is implied but not a discrete FINOS risk. |  | Data Pipeline
R-38 | L10 | Strategic misalignment & failed ROI | Business-outcome / ROI risk is above FINOS's model-centric scope. |  | Business Outcome
LAYER COVERAGE COUNT (live from register Stack Layer column)
Layer | # Risks
L1 | 2
L2 | 1
L3 | 3
L4 | 2
L5 | 6
L6 | 6
L7 | 2
L8 | 10
L9 | 4
L10 | 2
Verdict key: Covered = adequately addressed by existing risks ¦ Partial → Closed = thin coverage now reinforced ¦ Gap → Closed = absent in register, new risk added. Data-risk layers (L4-L5) shown in red per the architecture's elevated data-risk zone.